## Project Plan
Lear Project Plan | Critical | Task | Task | % | 2017-07-05
|  | Start | Finish | Completed |  | CEVA | CEVA
|  | Date | Date |  | Days to | Owner | Owner | Comments
Completion
PP Build Plan |  | 2017-04-10 | 2017-06-09 | 100% |  | Operations | Operations
Daily plan for PP build |  | 2017-04-10 | 2017-04-28 | 100% |  | David Gruss |  | 5/9 New v2 David will send from Robert
Outbound plan for PP build |  | 2017-05-01 | 2017-05-19 | 100% |  | David Gruss
Manual sequencing process validated |  | 2017-05-08 | 2017-05-12 | 100% |  | Luke Osborne | Matt Gumont
Update the manual process (complete outage update) |  | 2017-05-18 | 2017-06-09 | 100% |  | Luke Osborne |  | need resource
MHE received for PP build |  | 2017-05-01 | 2017-05-12 | 100% |  | Luke Osborne
Sequence racks in place for PP build |  | 2017-05-01 | 2017-05-12 | 100% |  | David Gruss |  | have a few racks of each
Signage in place for PP build |  | 2017-05-01 | 2017-05-12 | 100% |  | Luke Osborne
Material handlers dedicate to PP Build |  | 2017-05-08 | 2017-05-12 | 100% |  | Katrice Baughman | Luke Osborne | one person trained so far
Safety assessment |  | 2017-05-15 | 2017-05-19 | 100% |  | D’Arcy North | Kathleen Idland
Training for PP build |  | 2017-05-15 | 2017-05-22 | 100% |  | Luke Osborne
Go-live PP Build |  | 2017-05-26 | 2017-05-26 | 100% |  | Luke Osborne | Matt Gumont | NEW date 6/22???
Stage Gate 1 - Project Mobilization |  | 2017-03-30 | 2017-06-30 | 99% | -5
Complete Commercial Documentation |  | 2017-03-30 | 2017-06-30 | 99% | -5 | BD | BD
Facilities defined 12200 Westport Road, Louisville, KY 40245 |  | 2017-03-30 | 2017-03-30 | 100% |  | Taylor |  | Completed 5/15
Cost model complete |  | 2017-03-30 | 2017-04-05 | 100% |  | Ron Reinert | Chad Stokes
Cost model reviewed |  | 2017-03-30 | 2017-04-05 | 100% |  | Dorian Taylor | D’Arcy North
Pricing sent to Lear |  | 2017-04-06 | 2017-04-07 | 100% |  | Dorian Taylor
ICAP approved |  | 2017-04-06 | 2017-04-07 | 100% |  | Ron Fields | Dorian Taylor | ICAP-0002381 Lear KTP Sequencing is fully approved on 6/1
LOI signed (N/A) quicker to get the contract signed |  | 2017-05-15 | 2017-05-24 | 100% |  | Dorian Taylor | Lear | need LOI to start purchasing
Contract signed |  | 2017-03-30 | 2017-04-17 | 100% |  | Dorian Taylor |  | Signed by Lear 5/25
BU# Assigned 16800596 |  | 2017-04-17 | 2017-04-24 | 100% |  | Dorian Taylor |  | 16800596
KPI's reviewed |  | 2017-04-17 | 2017-06-30 | 0% | -5 | Darryl Spaulding | D’Arcy North
Receive PO From Lear |  | 2017-05-25 | 2017-06-30 | 0% | -5 | Dorian Taylor | D’Arcy North | Dondi Roberts-Parker
Develop Billing Template |  | 2017-05-25 | 2017-06-30 | 100% |  | Dorian Taylor | D’Arcy North | Dondi Roberts-Parker
Develop Billing Process |  | 2017-05-25 | 2017-06-30 | 100% |  | Dorian Taylor | D’Arcy North | Dondi Roberts-Parker
Plan Development |  | 2017-03-30 | 2017-04-07 | 100% |  | PIM | PIM
Project plan developed |  | 2017-03-30 | 2017-04-07 | 100% |  | Rob Friend
Project plan approved |  | 2017-03-30 | 2017-04-07 | 100% |  | Rob Friend
Assign Implementation Team |  | 2017-03-30 | 2017-03-30 | 100%
Operations owner assigned |  | 2017-03-30 | 2017-03-30 | 100% |  | D’Arcy North
Project team assigned |  | 2017-03-30 | 2017-03-30 | 100% |  | Rob Friend
Internal kickoff meeting held |  | 2017-03-30 | 2017-03-30 | 100% |  | Rob Friend
Customer kickoff meeting held |  | 2017-03-30 | 2017-03-30 | 100% |  | Rob Friend
Project communication plan developed |  | 2017-03-30 | 2017-03-30 | 100% |  | Rob Friend
Stage Gate 2 Finalize Requirements |  | 2017-03-29 | 2017-06-30 | 90% | -5
High Processes Complete |  | 2017-04-03 | 2017-04-24 | 100% |  | Solutions Design | Solutions Design
VSM complete |  | 2017-04-03 | 2017-04-24 | 100% |  | Venkat Ganesh
Warehouse processes Sequencing |  | 2017-04-03 | 2017-04-24 | 100% |  | Venkat Ganesh
Warehouse processes Non Sequencing |  | 2017-06-06 | 2017-06-30 | 0% | -5 | Venkat Ganesh | Luke Osborne
Warehouse processes EDI |  | 2017-06-06 | 2017-06-15 | 100% |  | Susan Patterson |  | used the ones from Lear, no changes needed
Requirements Complete |  | 2017-03-29 | 2017-06-30 | 99% | -5
Facility specifications complete |  | 2017-04-10 | 2017-06-30 | 95% | -5
Layout drafted |  | 2017-04-10 | 2017-04-25 | 100% |  | David Fondaw
Layout approved |  | 2017-04-14 | 2017-04-27 | 100% |  | David Fondaw
Storage requirements |  | 2017-04-14 | 2017-06-19 | 100% |  | David Fondaw
Slotting plan complete |  | 2017-04-14 | 2017-06-30 | 50% | -5 | David Fondaw
Equipment specifications complete |  | 2017-03-29 | 2017-03-29 | 100% |  | David Fondaw
Transportation specifications complete |  | 2017-03-29 | 2017-03-29 | 100% |  | David Fondaw
IT requirements complete |  | 2017-04-17 | 2017-05-22 | 100%
IT Business Requirements signoff |  | 2017-04-17 | 2017-05-12 | 100% |  | Susan Patterson
Reporting requirements |  | 2017-05-15 | 2017-05-22 | 100% |  | Susan Patterson
Procurement Requirements |  | 2017-04-10 | 2017-04-21 | 100%
Equipment purchasing requirements |  | 2017-04-10 | 2017-04-21 | 100% |  | David Fondaw
IT purchasing requirements |  | 2017-04-10 | 2017-04-21 | 100% |  | Chris Rhodes
Transportation purchasing requirements (if needed) |  | 2017-04-10 | 2017-04-21 | 100% |  | David Fondaw
Other purchasing requirements |  | 2017-04-10 | 2017-04-21 | 100% |  | David Fondaw
Manpower Requirements |  | 2017-03-30 | 2017-03-30 | 100%
Staffing plan complete |  | 2017-03-30 | 2017-03-30 | 100% |  | D’Arcy North
Hiring plan complete |  | 2017-03-30 | 2017-03-30 | 100% |  | D’Arcy North
Quality, Training, Safety and Security Requirements |  | 2017-04-10 | 2017-05-10 | 100%
Quality requirements defined |  | 2017-04-10 | 2017-05-10 | 100% |  | David GIlmore
Safety requirements defined |  | 2017-04-10 | 2017-05-10 | 100% |  | Kathleen Idland
Security requirements defined |  | 2017-04-10 | 2017-05-10 | 100% |  | Chris Shampine | Gary Wolf
Stage Gate 3 -Complete Systems and Processes |  | 2017-04-24 | 2017-08-14 | 25% | 40
Manpower Planning |  | 2017-05-15 | 2017-08-14 | 25% | 40
New employees hired |  | 2017-05-15 | 2017-08-14 | 25% | 40
WAP Complete |  | 2017-06-19 | 2017-06-30 | 100% |  | Katrice Baughman | Luke Osborne
SOA |  | 2017-05-15 | 2017-07-17 | 100%
Position posted |  | 2017-05-15 | 2017-05-19 | 100% |  | Katrice Baughman
Interivews |  | 2017-05-22 | 2017-06-23 | 100% |  | Katrice Baughman | Susan Patterson | Luke Osborne
Selection |  | 2017-06-26 | 2017-06-29 | 100% |  | Katrice Baughman | Susan Patterson | Luke Osborne
Offer extended |  | 2017-06-30 | 2017-06-30 | 100% |  | Baughman
SOA starts |  | 2017-06-30 | 2017-06-30 | 100% |  | Baughman |  | Mark Partyka started 5/30
Supervisor (1) |  | 2017-05-29 | 2017-07-31 | 100%
Position posted |  | 2017-05-29 | 2017-06-02 | 100% |  | Baughman
Interivews |  | 2017-06-05 | 2017-07-07 | 100% |  | Luke Osborne
Selection |  | 2017-07-10 | 2017-07-14 | 100% |  | Luke Osborne
Offer extended |  | 2017-07-14 | 2017-07-14 | 100% |  | Katrice Baughman
Supervisor starts |  | 2017-07-31 | 2017-07-31 | 100% |  | Katrice Baughman
Clerks (1 Inventory Clerk / 1 Operations Clerk) |  | 2017-06-12 | 2017-08-07 | 5% | 33 |  |  | Zack Perkins started 5/30
Position posted |  | 2017-06-12 | 2017-06-16 | 100% |  | Katrice Baughman
Interivews |  | 2017-06-19 | 2017-07-13 | 0% | 8 | Luke Osborne
Selection |  | 2017-07-14 | 2017-07-14 | 0% | 9 | Luke Osborne
Offer extended |  | 2017-07-14 | 2017-07-21 | 0% | 16 | Katrice Baughman
Clerks start |  | 2017-07-24 | 2017-07-24 | 0% | 19 | Katrice Baughman
Lead (1) |  | 2017-06-12 | 2017-08-07 | 25% | 33
Position posted |  | 2017-06-12 | 2017-06-16 | 100% |  | Katrice Baughman
Interivews |  | 2017-06-19 | 2017-07-01 | 75% | -4 | Luke Osborne
Selection |  | 2017-06-19 | 2017-07-01 | 0% | -4 | Luke Osborne
Offer extended |  | 2017-06-19 | 2017-07-01 | 0% | -4 | Katrice Baughman
Lead starts |  | 2017-07-05 | 2017-07-05 | 0% | 0 | Katrice Baughman
Warehouse staff (9) |  | 2017-05-16 | 2017-08-07 | 20% | 33 |  |  | 2 started 6/5
Position posted |  | 2017-05-16 | 2017-06-16 | 100% |  | Luke Osborne | Katrice Baughman
Interivews |  | 2017-05-16 | 2017-07-13 | 20% | 8 | Luke Osborne | Katrice Baughman
Selection |  | 2017-05-16 | 2017-07-14 | 20% | 9 | Luke Osborne | Katrice Baughman
Offer extended |  | 2017-05-16 | 2017-07-21 | 20% | 16 | Luke Osborne | Katrice Baughman
Warehouse staff start |  | 2017-05-16 | 2017-07-24 | 20% | 19 | Luke Osborne | Katrice Baughman
Facility and Equipment Readiness |  | 2017-04-24 | 2017-07-28 | 0% | 23
Equipment |  | 2017-04-24 | 2017-07-28 | 25% | 23
AFE's submitted |  | 2017-04-24 | 2017-04-28 | 100% |  | Mark Golden
Orders placed |  | 2017-05-01 | 2017-05-05 | 100%
Racking (everything) |  | 2017-05-01 | 2017-05-05 | 100% |  | Mark Golden |  | 6/1 received bid from SS, Have used racking 20 ft. upright by 48 inched depth
MHE |  | 2017-05-01 | 2017-05-05 | 100% |  | Mark Golden
Warehouse equipment |  | 2017-06-05 | 2017-07-11 | 0% | 6
Orders placed |  | 2017-06-05 | 2017-07-11 | 0% | 6 | Luke Osborne | Mark Golden
Signage |  | 2017-06-05 | 2017-07-11 | 0% | 6 | Luke Osborne | Mark Golden
Performance boards |  | 2017-06-05 | 2017-07-11 | 0% | 6 | Luke Osborne | Mark Golden
Work stations |  | 2017-06-05 | 2017-07-11 | 0% | 6 | Luke Osborne | Mark Golden
Other |  | 2017-06-05 | 2017-07-11 | 0% | 6 | Luke Osborne | Mark Golden
Equipment received |  | 2017-07-21 | 2017-07-28 | 0% | 23
Racking |  | 2017-07-21 | 2017-07-22 | 0% | 17 | Mark Golden
MHE (5) |  | 2017-07-24 | 2017-07-28 | 0% | 23 | Mark Golden
Warehouse equipment received |  | 2017-07-03 | 2017-07-18 | 0% | 13
Signage |  | 2017-07-03 | 2017-07-18 | 0% | 13 | Luke Osborne | Mark Golden
Performance boards |  | 2017-07-03 | 2017-07-18 | 0% | 13 | Luke Osborne | Mark Golden
Work stations |  | 2017-07-03 | 2017-07-18 | 0% | 13 | Luke Osborne | Mark Golden
Other |  | 2017-07-03 | 2017-07-18 | 0% | 13 | Luke Osborne | Mark Golden
IT system |  | 2017-04-24 | 2017-07-14 | 15% | 9
AFE's submitted |  | 2017-04-24 | 2017-04-28 | 100% |  | Chris Rhodes
Orders placed |  | 2017-05-05 | 2017-05-05 | 100% |  | Chris Rhodes
Servers |  | 2017-05-05 | 2017-05-05 | 100% |  | Chris Rhodes
Scanners |  | 2017-05-05 | 2017-05-05 | 100% |  | Chris Rhodes
Printers |  | 2017-05-05 | 2017-05-05 | 100% |  | Chris Rhodes
Computers |  | 2017-05-05 | 2017-05-05 | 100% |  | Chris Rhodes
Other |  | 2017-05-05 | 2017-05-05 | 100% |  | Chris Rhodes
IT hardware received |  | 2017-05-26 | 2017-07-14 | 10% | 9
Servers in Houston for config |  | 2017-05-26 | 2017-06-06 | 100% |  | Christman | Chris Rhodes | 6/26 date from Dell but already have 3 of the 5 in TX on 6/20. Received the other 2 on 6/26.
Servers in KTP for install |  | 2017-06-12 | 2017-06-12 | 0% | -23 | Chris Rhodes | Mark Partka | ETA 7/7, dave in Louisville 7/10
Scanners |  | 2017-06-12 | 2017-07-14 | 0% | 9 | Chris Rhodes | Mark Partka
Printers |  | 2017-06-12 | 2017-07-14 | 0% | 9 | Chris Rhodes | Mark Partka
Computers |  | 2017-06-12 | 2017-07-14 | 0% | 9 | Chris Rhodes | Mark Partka
Other |  | 2017-06-12 | 2017-07-14 | 0% | 9 | Chris Rhodes | Mark Partka
Document Processes |  | 2017-06-05 | 2017-07-14 | 0% | 9
Work Instructions complete |  | 2017-06-05 | 2017-07-14 | 0% | 9 | Luke Osborne |  | Will be able to use WI from Quebec (Justin). IT will have PKMS & Insequence WI’s.
Safety and Training Ready |  | 2017-06-05 | 2017-08-04 | 0% | 30
Safety program complete |  | 2017-06-05 | 2017-07-28 | 0% | 23 | Kathleen Idland
Training program and materials complete |  | 2017-07-10 | 2017-08-04 | 0% | 30
Training Plan developed |  | 2017-07-10 | 2017-07-21 | 0% | 16 | Erin Massey | Luke Osborne
Trainers identified |  | 2017-07-10 | 2017-07-21 | 0% | 16 | Erin Massey | D’Arcy North
Training Schedule developed |  | 2017-07-10 | 2017-07-21 | 0% | 16 | Erin Massey | Luke Osborne
Training material complete |  | 2017-07-10 | 2017-07-21 | 0% | 16 | Luke Osborne | Erin Massey
Ford Training (WebEx or classes in Dearborn) |  | 2017-07-05 | 2017-07-28 | 0% | 23 | Luke Osborne | D’Arcy North | per David Gruss (Covisint)
System Requirement Definition and Design |  | 2017-05-01 | 2017-07-07 | 0% | 2
Development |  | 2017-05-01 | 2017-07-07 | 0% | 2 | Susan Patterson
Stage Gate 4 - Testing and Training |  | 2017-06-12 | 2017-08-25 | 0% | 51
Set-up Facility and equipment |  | 2017-06-12 | 2017-08-25 | 0% | 51
Facility set-up |  | 2017-06-12 | 2017-07-28 | 5% | 23
ID Facility setup tiger team |  | 2017-06-12 | 2017-06-23 | 100% |  | D’Arcy North | Jerry Ewersmann
Security upgrades (as needed) |  | 2017-07-03 | 2017-07-14 | 0% | 9 | Chris Shampine | Gary Wolf
Racking reconfigured/Installed |  | 2017-07-24 | 2017-07-28 | 0% | 23 | Mark Golden | Storage Solutions
Workstations setup |  | 2017-07-03 | 2017-07-28 | 0% | 23 | Luke Osborne
Sequence racks received and setup |  | 2017-07-03 | 2017-07-28 | 0% | 23 | Chris Rhodes | Mark Partyka
Floor markings and signage installed |  | 2017-07-03 | 2017-07-28 | 0% | 23 | Luke Osborne
Performance boards ready |  | 2017-07-03 | 2017-07-28 | 0% | 23 | Luke Osborne
MHE set-up and ready |  | 2017-07-31 | 2017-08-04 | 0% | 30 | Luke Osborne | Mark Golden
IT hardware installed |  | 2017-06-13 | 2017-07-25 | 0% | 20
Insequence Servers installed |  | 2017-06-13 | 2017-07-25 | 0% | 20 | Chris Rhodes | Dave Saucier
Final facility check |  | 2017-08-01 | 2017-08-04 | 0% | 30 | Chris Rhodes | Luke Osborne
Test IT Systems and Operational Processes |  | 2017-07-07 | 2017-08-18 | 0% | 44
SIT Testing |  | 2017-07-07 | 2017-07-20 | 0% | 15 | Susan Patterson
Train the Trainer/SME |  | 2017-08-07 | 2017-08-18 | 0% | 44 | Susan Patterson
UAT end-to-end |  | 2017-07-24 | 2017-08-04 | 0% | 30 | Susan Patterson
Training |  | 2017-07-24 | 2017-08-04 | 0% | 30
Training completed |  | 2017-07-24 | 2017-08-04 | 0% | 30 | Luke Osborne | Erin Massey
Certifications complete |  | 2017-07-24 | 2017-08-04 | 0% | 30 | Luke Osborne | Erin Massey
Training validation |  | 2017-07-24 | 2017-08-04 | 0% | 30 | Luke Osborne | David GIlmore
Stage Gate 5 - Go-LIVE |  | 2017-07-10 | 2017-09-08 | 0% | 65
Transportation and Dock Plan |  | 2017-07-10 | 2017-08-11 | 0% | 37
Inbound / Outbound Planning |  | 2017-07-10 | 2017-07-28 | 0% | 23 | David Fondaw | Luke Osborne
Dock Plan / Packout |  | 2017-07-31 | 2017-08-11 | 0% | 37
Receiving MP1 Build |  | 2017-08-07 | 2017-08-25 | 0% | 51 |  |  | May need to ship the of 8/7
Begin receiving material / build inventory |  | 2017-08-07 | 2017-08-25 | 0% | 51
Inventory checked |  | 2017-08-07 | 2017-08-25 | 0% | 51
Go Live Readiness |  | 2017-08-07 | 2017-09-08 | 0% | 65
Ford Launch readiness review (LRR) John Curtright |  | 2017-05-30 | 2017-08-07 | 0% | 33
SharePoint Access- Ford MP&L LRR with R59C2 Lear CEVA |  | 2017-05-30 | 2017-06-15 | 100% |  |  |  | Luke will get with Lisa Fox
Launch readiness and support |  | 2017-08-04 | 2017-09-08 | 0% | 65 |  |  | Bring people from KCAP to support.
Mock Go-live - / Day in the Life (DILO) |  | 2017-08-04 | 2017-08-07 | 0% | 33
KPI's and reports ready to be produced |  | 2017-08-04 | 2017-08-07 | 0% | 33
Performance monitoring ready |  | 2017-08-04 | 2017-08-07 | 0% | 33
Reporting ready |  | 2017-08-04 | 2017-08-11 | 0% | 37
% COMPLETE & DAYS TO IP Build GO LIVE | * |  | 2017-05-18 | 100% |  |  |  | 2 racks
% COMPLETE & DAYS TO PP Build GO LIVE | * |  | 2017-05-26 | 100% |  |  |  | Ford’s 1st build is May 30th
% COMPLETE & DAYS TO MP1 GO LIVE | * |  | 2017-08-07 | 51.99% | 33 |  |  | Start Build 8/28, ship 8/24 & 8/25, Sequence 8/21. Receive 8/14
% COMPLETE & DAYS TO Serial GO LIVE | * |  | 2017-09-08 | 51.99% | 65 |  |  | 9/25?

## Contact List
Functional Area | CEVA Representative | Email | Phone | Functional Area | Lear Representative | Email | Phone
Business Development / VP Contract Logistics Automotive | Holger Wilhelm | holger.wilhelm@cevalogistics.com | 734-262-4174 | Regional Warehouse Operations Manager - E-Systems | David Gruss | DGruss@lear.com | 574-930-6753
Business Development / Director, Solution Development | Dorian Taylor | dorian.taylor@cevalogistics.com | 734-229-1717 |  | Dondi Robert-Parker
Legal / Legal Counsel | Janet Brown | janet.brown@cevalogistics.com | 281-618-3534 |  | David McKee
Accounting / Finance | Ron Fields | ronald.fields@cevalogistics.com | 904-545-1213 |  | Jessica Handal Lopez
Project Management / Vice President, | Glen Clark | glen.clark@cevalogistics.com | 904-545-1544 |  | Angela Lopez Acosta
Project Management / Manager, New Business Implementations | Robert Friend | robert.friend@cevalogistics.com | 904-386-0445 |  | Jose Avila Dasilva
Project Management / Manager, New Business Implementations | Jerry Ewersmann | gerard.ewersmann@cevalogistics.com | 832-878-6697 |  | Carlos Luna
Operation / V.P. Automotive Operations | D’Arcy North | darcy.north@cevalogistics.com | 980-225-4014 |  | Claudia Deleon
Operations / District General Manger | Darryl Spaulding | darryl.spaulding@cevalogistics.com | 502-883-6368 |  | Angelica Torres Valadez
Operations / General Manager | Matthew Gumont | matthew.gumont@cevalogistics.com | 502-442-0484 |  | Robert Battaglia
Operations/ Assistant Contract Manager | Luke Osborne | mervin.osborne@cevalogistics.com | 502-299-0692 |  | Reina Guevara Rodas
Solutions Design / Vice President | Chad Zollman | chad.zollman@cevalogistics.com | 616-799-6445 |  | Maiela Rivera Pineda
Solutions Design / Logistics Manager | Ron Reinert | ron.reinert@cevalogistics.com | 313-242-1602
Solutions Design / Logistics Engineer | Dave Fondaw | dave.fondaw@cevalogistics.com | 248-663-6370
IT / VP IT Customer Engagement | Susan Schmidt | susan.schmidt@cevalogistics.com | 904-928-1413
IT / Director Program Management, Project Manager | Susan Patterson | susan.patterson@cevalogistics.com | 904-449-1596
IT / Manager WMS Competency Center, Technical Manager | Brian Finch | brian.c.finch@cevalogistics.com | 615-372-4406
IT / Functional Analyst | Dave Saucier | dave.saucier@cevalogistics.com | 636-283-1055
IT / Manager | Thomas Gehret | thomas.gehret@cevalogistics.com | 904-996-1268
IT / Delivery Lead - CL Solutions - Americas | Devon Gayle | devon.gayle@cevalogistics.com | 404-807-1850
IT / SOA | Roy Mankin | roy.mankin@cevalogistics.com | 440-653-7095
IT Purchasing / Infrastructure & Implementation Management | Chris Rhodes | katrice.baughman@cevalogistics.com | 904-535-6154
HR / HR Coordinator | Katrice Baughman | chris.rhodes@cevalogistics.com | 502-873-3120
Procurement / Sr. Manager Procurement | Mark Golden | mark.golden@cevalogistics.com | 281-618-3280
Procurement Vehicle Maintenance / Senior Asset Control Specialists | Erin Stallings | erin.stallings@cevalogistics.com | 832.348.4974
Quality/Director, Quality Assurance | David Gilmore | david.gilmore@cevalogistics.com | 904-254-1172
Quality/Corporate Manager, Quality/Operations Improvement | Tommy Williams | tommy.williams@cevalogistics.com | 904-316-0360
BPE / Director, Business Process Excellence | Casey Pratt | casey.pratt@cevalogistics.com | 662-420-1497
Training / Operations Training Specialist | Erin Massey | ErinKelli.Massey@cevalogistics.com | 904-564-1120
Facility / Manager, Properties | Joanne Wright | joanne.wright@cevalogistics.com | 904-624-1427
Safety / Regional Safety Manager – HSE, Nortam | Greg Shaver | greg.shaver@cevalogistics.com | 832-790-2254
Security / Director | Gary Wolf | gary.wolf@cevalogistics.com | 901-547-6740
Security / Director FM | Chris Shampine | chirs.shampine@cevalogistics.com | 832-549-3615